Project plan to establish a UArctic Thematic Network in the Environmental Humanities

Host: UiT The Arctic University of Norway

Introduction

Critical geopolitical and natural tensions are manifest in Sápmi, where we are situated, and the broader northern regions. The high North has shifted – and is still shifting – from being perceived as a peripheral region to being central in contemporary discourse, particularly in terms of military activity, geopolitics, legal uncertainty, resource extraction, colonialism and its residues, and climate change. These changes and conflicts manifest across many levels and scales, from the individual body to the local, regional, national, and planetary. Addressing these challenges can only be addressed by an integration across disciplines, including the arts and humanities. A UArctic Thematic Network in the Environmental Humanities, grounded in interdisciplinary collaboration, can engage more fully with issues pertaining to social, ecological, climatic, legal, cultural, and decolonial contexts.

The Environmental Humanities has emerged over the past decade as a critical field addressing pressing environmental challenges. In 2021 a group of researchers from UiT The Arctic University of Norway together with local artists established an Environmental Humanities network, and in January 2025 was awarded the recognition of research group status by the Arctic University Museum of Norway and Academy of Fine Arts (UMAK). The group has four years of experience in organising diverse and inclusive activities such as reading groups, thematic presentations and discussions, seminars, walk & talk sessions, skills circles, and film viewings (see https://uit.no/research/environmentalhumanities). It also has a strong support network for early career scholars. Environmental and Indigenous interests are inherent to our teaching and research, which includes landscape architecture, art history, health, law, gender studies, cultural studies, media studies, future studies, geosciences, musicology, literature, archaeology, anthropology, tourism, and more.

1. Purpose and overall goal of the project

The interdisciplinarity of the UiT Environmental Humanities Research Group underscores the role of the arts, humanities, and social sciences in tackling environmental challenges while fostering and strengthening dialogue with the natural sciences. Having established a sound foundation within UiT The Arctic University of Norway, the overall goal is to build up, connect with, and learn from an international thematic network through research, teaching, innovation, mobility, outreach, and impact under the auspices of the University of the Arctic. The thematic network is situated in the high North (with plans to reach out to the global south in the future) and will serve as a platform for sharing and exploring current and future environmental issues and address conflicts connected to territory and recourses, values and culture, and human/non-human relations. The three thematic strands of the thematic network, with their corresponding goals, deliverables, impacts, and monitoring (see table) are not mutually exclusive, but entangled in the shared values of UArctic and the Environmental Humanities.

2. List and description of concrete deliverables (timeline in separate document and application form)

| Thematic strands (S) | Overall goals (G) | Deliverables/outputs (D) | Anticipated impact (I) | Monitoring mechanisms (M) |
| --- | --- | --- | --- | --- |
| S1. Environmental humanities, sustainability, and planetary health | G1. Provide a fundamental critique of colonialism, extractivism, imperialism, patriarchy, capitalism, and other forms of oppression that are embroiled in environmental issues | D1.1. Develop two interdisciplinary collaborative research projects involving at least two partners (one project per year) D1.2. Network meetings (3 per year, blended formats, revolving host institutions) including project workshops D1.3. Develop at least one co-creative outreach workshop with societal impact (e.g. multimedia exhibition at the Academy of Art, Tromsø) | I1.1. Cross-disciplinary participation at all stages, from project generation to research and dissemination I1.2. Participation from partners, with a broad spectrum of disciplines and nationalities represented I1.3. Engagement of health, journalism, policymakers, NGOs, and cultural sector (leading to further activities e.g. a travelling exhibition) | M1.1. Peer evaluation, advisory board M1.2. Advisory board M1.3. Local consultations/responses, advisory board |
| S2. Indigenous, decolonial, gender, and feminist perspectives in interdisciplinary collaboration | G2. Break down dualities such as human/non-human, remote/situated, nature/culture, art/science, we/them, and exclusion/inclusion | D2.1. 5 ECTS-point graduate module (with Memorial University (CA), Westfjords (IS), and others) and cross-partner involvement in existing graduate programmes D2.2. add at least two active Indigenous-majority partners D2.3. World Cafés (online, two per semester) | I2.1. Progress towards development of UA master’s I2.2. Increase Indigenous/minority participation in the thematic network and projects (D1.1.) I2.3. Knowledge exchange, networking, peer support: ripple affect | M2.1. NOKUT / UArctic evaluation; student evaluations; teacher reflections M2.2. Advisory board M2.3. Attendance; other activities born from the cafés; increased participation in the thematic network |
| S3. Knowledge production, creativity, and communication as contribution to peace in the Arctic | G3. Inclusion of humanities and artistic research perspectives at all stages and strengthen collaborations across the environmental humanities | D3.1. Support the establishment of the Memorial University Center for the Environmental Humanities (MUNL, Canada) D3.2. At least two cross-disciplinary open access peer-reviewed research articles D3.3. Engagement with local artists/journalists (e.g. in workshop/exhibition: D1.3.) D3.4. Establish student/researcher mobility and knowledge exchanges D.3.5. Open access interdisciplinary research methodologies/guide; establishment of and special issue in Creative (Septentrio) | I3.1. Increased teaching/research into the Environmental Humanities in Newfoundland and Labrador (and UA partners) I3.2. Increased visibility of cross-disciplinary research in the Environmental Humanities I3.3. increased representation of non-academic partners to become a regular event within local community I3.4. North2North/EUGLOH programmes, network meetings I3.5. adaptation in other disciplines/projects | M3.1. Advisory board, internal evaluation at MUNL M3.2. Cross-disciplinary collaboration, article metrics M3.3. Attendance, reviews (e.g. local press), advisory board M3.4. Advisory board and reflections from exchange participants M3.5. Participation, peer review, downloads, altmetrics, citations, development of open research data (where appropriate) |

3. Description of project activities

Strand 1: Environmental Humanities, sustainability and planetary health

This strand will engage in reframing and addressing challenges of sustainability, transformative change and planetary health from the perspective of the environmental humanities, focusing particularly on the sociocultural challenges at the root of today’s inseparable health, social, and ecological crises. This strand has the development of the thematic network at its core, as it contains deliverables that are directly linked to the network’s progress: collaborative cross-disciplinary research projects (D1.1.), network meetings (D1.2.), and outreach projects with broad impact (D1.3.).

Strand 2: Indigenous, decolonial, gender and feminist perspectives in interdisciplinary collaboration

Indigenous, decolonial, gender, and feminist perspectives are essential to our definition of the Environmental Humanities, which also seeks to confront and break down harmful dualities. This strand will increase and diversify the participation in the thematic network from across the Arctic and its peoples through active recruitment and involvement of Indigenous (and other minority) partners (D2.2.), that will feed into the research projects (D1.1., D1.3.) and outputs (D3.2., D3.5.). The World Cafés (D2.3.) will act as informal meeting and networking opportunities, held online to maximise participation and reduce carbon emissions, and will act as points of contact between the more formal network meetings (D1.2.). This strand is also responsible for the development of teaching programmes (D2.1.), initially graduate modules with a view to the longer-term goal of a UArctic master’s in the Environmental Humanities (I2.1., beyond the duration of this funding call).

Strand 3: Knowledge production, creativity, and communication as contribution to peace in the Arctic

The challenges facing the Arctic (and the planet) today are not solvable through monodisciplinary work, or by research alone. This strand therefore has cross-disciplinarity at its core, together with dissemination, outreach, and mobility. This strand brings together international peer-reviewed academic research (D3.2.) with local development and engagement both in academia (D3.1.) and in the local communities (D3.3.). These are not exclusive areas, thus there is an important mobility element (D3.4.), together with the establishment of UiT’s online research journal/portal Creative (Septentrio) (D3.5.), where members of the network will collaborate with the UiT University Library, the Centre for Arctic Humanities, and other research groups to provide a portal for publishing experimental and creative research outputs, methodological reflections, and guides (e.g. to fieldwork).

4. UArctic strategic plan and the six UArctic values

4.1 Circumpolar

Although based out of Sápmi (the areas that fall in Norway, Sweden, and Finland), we have confirmed project partners in Canada, Iceland, Svalbard, the UK, and Oslo. It is one of the primary goals of establishing the thematic network to expand this representation to include more partners from within and outside of the circumpolar region.

4.2 Inclusive

We address the need to integrate many forms of knowledges and knowing in two of our goals (G1. and G3.). While being sensitive to languages, culture, gender, age, and other markers of difference, we privilege co-creativity and other collective practices that combine knowledges from across disciplines and from outside academic institutions. Living, working, and creating new knowledge in difference together is the foundation of what we do. We have members and partners with a broad range of expertise in gender studies, healthcare, law, anthropology, ethnomusicology, and more, all of which develop a focus on inclusivity.

4.3 Respectful

Indigenous (and decolonial) perspectives are embedded in the Environmental Humanities, and one of our main goals is to break down barriers and dualities (G2.). The host institution, UiT The Arctic University of Norway, is located in Sápmi, and has a strong research and teaching commitment to Indigenous issues. Indigenous integration is an ongoing and multiway process, and thus will be regularly re-evaluated as part of the quality control processes. There are several areas/projects already taking place at UiT under the auspices of the Environmental Humanities Research Group (e.g. Britt Kramvig and Tarja Salmela’s ongoing projects on tourism and place-sensitive sustainability in Sápmi, Filip Maric’s application to NFR for a project on Indigenous knowledge and planetary health, the artistic research project ARcTic Sustain, the NFR-funded project Arctic Frontiers, and the PhD projects in Indigenous law, Law of the sea, ethnomusicology, art history, and linguistics).

4.4 Collaborative

Members within the research group at UiT have extensive and diverse experience with collaborative work and projects, and collaboration is embedded into our goals for the network (G2., G3.). Based on our continuing participation work (e.g. the Master’s in Landscape Architecture, the NFR project Arctic Frontiers, the Centre for Arctic Humanities, and the activities of the Environmental Humanities Research Group), the development of the thematic network will facilitate collaborative processes through meetings (D1.2., D2.3.), workshops and exhibitions (D1.3.), projects (D1.1.), teaching (D2.1., D3.1.), publications (D3.2., D3.5.), and outreach (D1.3., D3.3.).

4.5 Open

Openness runs across the network’s activities. In research and publication, we are currently collaborating with UiT University Library to establish the open platform Creative (Septentrio), which is an integral part of our activities (D3.5., I3.5., M3.5.), and our other research outputs will also be open access (D3.2.). The planned teaching collaborations (D2.1., D3.1.) and exchanges (D3.4.), as well as networking (D2.3.), are both inherently open, and designed to increase future participation (I2.2., I2.3., I3.1., I3.4.). Last but not least, our outreach activities (D1.3., D3.3.) are geared towards both immediate and long-term openness and impact (I1.3., I3.3.) to establish meaningful and lasting connections and openness.

4.6 Influential

Project participants already have established links to local policymakers with high impact, for example the kittiwake hotels in Tromsø (part of research group member Kåre Grundvåg’s PhD project), the kittiwake integration programmes in North East England (project partner Helen Wilson, University of Durham), the collaboration projects by research group members in the law of the sea (Faculty of Law, UiT), together with the place-sensitive tourism projects and landscape architecture programme already mentioned above. In addition, our strong focus on the arts (e.g. existing collaborations with professional groups such as Vokal Nord and UArctic World Ensemble, and our home in The Arctic University Museum and Academy of Fine Arts) provides a natural meeting point for policymakers, communities, and academic institutions. Finally, our partnership with the professional climate and science journalist Brett Simpson will ensure not only broad coverage of our activities, but more importantly the development of lasting connections with NGOs and policy institutions such as Arctic Indigenous Youth, GRID-Arendal (Arendalsuke), and the Arctic Council (I1.3., I3.3.).

5. Project outcomes, target groups, and impacts

The establishment of a UArctic Thematic Network in the Environmental Humanities and the setting in motion of its activities will have a lasting impact on the circumpolar world. For the target group of academic institutions (including academic faculty, staff, and students), the anticipated impacts include increased cross-disciplinary collaboration at all stages of research, from project generation, the research process, and outreach (I1.1., I1.2., I1.3.). It is particularly important that other target groups are represented too, e.g. local artists, journalists, and the cultural sector (I1.3., I3.3.), and that we continuously work towards increased participation from Indigenous and other minority groups (I2.2.). We do not see outputs and impact as necessarily separate; rather, our goal is to integrate impact planning at all stages, for example the integration of the peer-reviewed academic publications (D3.2.), the creative research outputs (D3.5.), the outreach activities (the participation from the cultural/health sectors (D3.3.), and the exhibition/workshop (D1.3.)). This will ensure that the target group of the broader Arctic communities is engaged from the start, such that their (our) needs will help develop the network activities. Of particular importance here is our engagement of a professional journalist, artists, and health workers of various nationalities and backgrounds (I1.3., I2.2.), such that our activities will become anchored in the local communities as regular events beyond the first two-year funding period (I3.3.). In addition, the target group of students is important: by establishing international Environmental Humanities programmes between partners (D2.1., D3.1.) and exchanges (D3.4.), the links between institutions, countries, and communities will continue to develop and grow even as individual student groups graduate (this also applies to professionals moving on in their careers: the connections will remain, even if the individuals change). This application and the thematic network is thus a first phase of an important movement to firmly integrate the Environmental Humanities in the Arctic, and to increase the impacts it can have for the communities, the land, and the peace and sustainability of the region.

6. Quality control, communication plan, and project sustainability

To ensure quality in this network and to help monitor the activities and goals, we propose the establishment of an advisory board of five members (see application form) who have experience in the Environmental Humanities. Our proposed indicators of quality include (but are not limited to) progress towards the development of the network (M1.1.–M1.3.), collaboration across disciplines and institutions (M1.1., M2.1.–M2.3., M3.2., M3.3.), impact on Arctic communities (M1.3., M3.3, M2.3.), publications (M3.2., M3.5), ethical issues (M1.1.), outreach activities (M1.3., M3.3.), student participation in and feedback on new courses (M2.1.); in short, the added value of the new thematic network for the partner institutions and for the high North more broadly. The advisory board will meet at least twice per year (moving to annually once the network is established) with leaders from each partner institution. In addition, the board will provide feedback and advice on the further development of the network, read and comment upon reports of the network activities, act as a sounding board for new ideas, and facilitate the success of the network’s long-term impact. Meetings between advisory board and partners 2–4 times per year will track progress of shared activities in relation to the set goals, provide feedback and advice on proposed projects and funding applications, and monitor and advise the integration of impact activities.