Project to establish a UArctic Thematic Network in the Environmental Humanities

Host: UiT The Arctic University of Norway

Activity/deliverables timeline

|  | Activity/strand | Autumn 2025 | Spring 2026 | Autumn 2026 | Spring 2027 |
| --- | --- | --- | --- | --- | --- |
| D1.1. | Develop two interdisciplinary collaborative research projects involving at least two partners (one project per year) |  |  |  |  |
| D1.2. | Network meetings (3 per year, blended formats), including advisory board meetings. Two hybrid meetings will be hosted in Tromsø. We propose Autumn 2025 and Spring 2027. | Hybrid | Online Hybrid | Hybrid | Online Hybrid |
| D1.3. | Develop at least one co-creative outreach workshop with societal impact (e.g. exhibition at the Academy of Art, Tromsø) |  | Planning | Exhibition | Evaluation |
| D2.1. | 5 ECTS-point graduate module (with Memorial University (CA), Westfjords (IS), and others) and cross-partner involvement in existing graduate programmes | Planning | Guest lectures | Module delivery | Evaluation |
| D2.2. | Add at least two active Indigenous-majority partners |  |  |  |  |
| D2.3. | World cafés (online, two per semester) |  |  |  |  |
| D3.1. | Support the establishment of the Memorial University Center for the Environmental Humanities (MUNL, Canada) |  |  |  |  |
| D3.2. | At least two cross-disciplinary open access peer-reviewed research articles |  |  |  |  |
| D3.3. | Engagement with local artists/journalists (e.g. in workshop/exhibition and podcast episode: D1.3.) |  |  |  |  |
| D3.4. | Establish student/researcher mobility and knowledge exchanges |  |  |  |  |
| D3.5. | Open access interdisciplinary research methodologies/guide; establishment of and special issue in Creative (Septentrio) |  | ‘Creative (Septentrio) |  | Research guides |