Project to establish a UArctic Thematic Network in the Environmental Humanities 
Host: UiT The Arctic University of Norway 
Activity/deliverables timeline

	
	Activity/strand
	Autumn 2025
	Spring 2026
	Autumn 2026
	Spring 2027

	D1.1.
	Develop two interdisciplinary collaborative research projects involving at least two partners (one project per year) 

	
	
	
	

	D1.2.
	Network meetings (3 per year, blended formats), including advisory board meetings. Two hybrid meetings will be hosted in Tromsø. We propose Autumn 2025 and Spring 2027. 

	Hybrid

	Online
Hybrid

	Hybrid

	Online
Hybrid


	D1.3.
	Develop at least one co-creative outreach workshop with societal impact (e.g. exhibition at the Academy of Art, Tromsø) 

	
	Planning

	Exhibition

	Evaluation


	
	
	
	
	
	

	D2.1.
	5 ECTS-point graduate module (with Memorial University (CA), Westfjords (IS), and others) and cross-partner involvement in existing graduate programmes  


	Planning

	Guest lectures

	Module delivery

	Evaluation


	D2.2.
	Add at least two active Indigenous-majority partners 
	
	
	
	

	D2.3.
	World cafés (online, two per semester) 
	
	
	
	

	
	
	
	
	
	

	D3.1.
	Support the establishment of the Memorial University Center for the Environmental Humanities (MUNL, Canada) 

	
	
	
	

	D3.2.
	At least two cross-disciplinary open access peer-reviewed research articles 

	
	
	
	

	D3.3.
	 Engagement with local artists/journalists (e.g. in workshop/exhibition and podcast episode: D1.3.)

	
	
	
	

	D3.4.
	Establish student/researcher mobility and knowledge exchanges 
	
	
	
	

	D3.5.
	Open access interdisciplinary research methodologies/guide; establishment of and special issue in Creative (Septentrio)

	
	‘Creative (Septentrio)

	
	Research guides




